## Sheet1
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Event Recommendation System
PROJECT SPONSOR | Cloud Counselage Pvt Ltd
PROJECT MANAGER | Jayanth G S
EXPECTED START DATE | 15/06/2020
EXPECTED COMPLETION DATE | 31/07/2020
ESTIMATED COST
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE | The main objective of the project is to develop an application where employers can get recommendation with the events which are in their domain. This application will help the employees of Cloud Counselage to secure a event in their domain.
BUSINESS CASE | Over the years, Cloud Counselage has been on a mission to develop and groom freshers and professionals PAN India to become IT and Management pioneers. To accomplish this mission, we have come up with a solution, a application will list down all the events in their domain to increase their skills in their interested domain.
GOALS/METRICS | To create a trusted portal for employees to get invites of events of their interest.
EXPECTED DELIVERABLES | A portal which will benefit the employees to see the events in their interested domains.
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE | apply to events which are in their domain
OUTSIDE OF SCOPE | cannot apply to event using this application.
PROJECT RESOURCES AND COSTS
PROJECT TEAM | Nikita Mahajan
SUPPORT RESOURCES | Laptop
SPECIAL NEEDS
PROJECT BENEFITS AND CUSTOMERS
PROCESS OWNER | Nikita Mahajan
KEY STAKEHOLDERS | Jayanth G S, Nirbhey Singh Pahwa
END CUSTOMER | Cloud Counselage
EXPECTED BENEFIT
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS | Techical risk:Unmet requirements-forgetting to include a single requirement can cost us time & budget overhead, or worse, poor website quality. Resource risk:Uncertainty in resource availability: Interns might go on leave on commencement of university exams. Due to the COVID-19 outbreak, the exact examination dates are not available.On team change over, new members needs to get trained and it's time-consuming.
ASSUMPTIONS | Will help the employees to get to know about the events they are interested in.
CONSTRAINTS | Very stringent time for the completion of the project.