## Sheet1
PROJECT PLAN FOR EXECUTION PHASE
PROJECT NAME | Event Recommendation System
PROJECT MANAGER | JAYANTH G S |  | EXECUTION PHASE START DATE: |  | 06-15-2020
PROJECT DELIVERABLE |  |  | EXECUTION PHASE END DATE: |  | 07-31-2020
PROJECT SCOPE
PROJECT START DATE | 06-15-2020
PROJECT END DATE | 07-31-2020
OVERALL PROGRESS | In Progress
PARENT FEATURE | FEATURES | REQUIRED TIME (IN HRS) | START DATE | END DATE | DURATION IN DAYS | STATUS
1. Initiation | 1.1 Understand the SDLC life cycle | 5 | 06-15-2020 | 06-18-2020 | 3 | COMPLETED
| 1.2 Understand the Problem Statement | 5 | 06-15-2020 | 06-18-2020 | 3 | COMPLETED
| 1.3 Going through Project Methodology | 5 | 06-15-2020 | 06-18-2020 | 3 | COMPLETED
2. Documentation | 2.1 project charter | 10 | 06-18-2020 | 06-23-2020 | 5 | COMPLETED
| 2.2 design model for project | 15 | 06-18-2020 | 06-23-2020 | 5 | COMPLETED
| 2.3 SRS document | 15 | 06-18-2020 | 06-23-2020 | 5 | COMPLETED
3. Planning | Create a Project Plan | 20 | 06-23-2020 | 06-28-2020 | 5 | COMPLETED
4. Execution | 4.1 Studying Problem Statement | 5 | 06-28-2020 | 06-30-2020 | 2 | COMPLETED
| 4.2 Studying the dataset and its features | 10 | 06-30-2020 | 2020-05-07 | 5 | COMPLETED
| 4.3 Finalizing method or algorithm to solve | 20 | 2020-05-07 | 07-15-2020 | 10 | COMPLETED
| 4.4 coded the method (nlp) get desired output | 20 | 07-15-2020 | 07-25-2020 | 10 | COMPLETED
5. Documentation | make required documents and report for project | 10 | 07-25-2020 | 07-30-2020 | 5 | COMPLETED