## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 1 | 0 | 0 | 0 | 0 | 0
| Project title: | Event Recommendation System |  | Project Id: |  | Project Manager: | JAYANTH G S |  |  | Assumption | 1 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 2 | 0 | 0 | 0 | 0 | 0
|  |  |  | Last Updated date: | 07-31-2020 | Project Team Lead: |  |  |  | Dependency | 0 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 4 |  |  |  |  | 0
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Assumption | assuming that the given data is accurate | impact on project efficiency | have a dedicated team for dataset | Project Manager | Moderate |  | Closed | Risk
2 | Issue | data adding | we have to manually add data to dataset for that whole dataset changes | have a method for adding data automatically to dataset | Project Manager | High |  | Closed | Assumption
3 | Risk | Build a proper project plan to ensure all the features are included and a certain implementation procedure is followed | Project Failure | Project Plan | Project Manager | Critical |  | Closed | Issue
4 | Issue | Unavailability of resources | Project Failure | Ensure proper working of hardware and all availability of the required softwares | Project Manager | Moderate |  | Closed | Dependency
5
6 | [8 empty] | Open
7 | [8 empty] | Closed
8
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24